## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | start
1 | first |  |  | FS2 | 2018-05-02 08:00 | 2018-05-03 08:00 | 1d | Programmers[1.00 #1] | 0 | 975 | 0 | 0 | 0
2 | second |  | 1FS | FS3 | 2018-05-03 08:00 | 2018-05-05 08:00 | 2d | Programmers[1.00 #2] | 0 | 28 | 0 | 0 | 0
3 | third |  | 2FS | FS4 | 2018-05-05 08:00 | 2018-05-08 08:00 | 3d | Technicians[1.00 #3] | 0 | 388 | 0 | 0 | 0
4 | fourth |  | 3FS | FS5 | 2018-05-08 08:00 | 2018-05-12 08:00 | 4d | Sales representatives[0.50 #2] | 0 | 4760 | 0 | 0 | 0
5 | fifth |  | 4FS | FS6;FS7;FS8;FS9;FS10 | 2018-05-12 08:00 | 2018-05-12 13:00 | 5h | Secretary;Programmers | 0 | 59860 | 0 | 0 | 0
6 | sixth |  | 5FS | FS7 | 2018-05-12 13:00 | 2018-05-12 19:00 | 6h | Marketing manager | 0 | 70 | 0 | 0 | 0
7 | seventh |  | 6FS;5FS | FS8 | 2018-05-12 19:00 | 2018-05-19 19:00 | 7d | Secretary;Programmers;IT Manager; Analyst programmer | 0 | 44 | 0 | 0 | 0
8 | eighth |  | 5FS |  | 2018-06-01 08:00 | 2018-06-08 08:00 | 8d | Marketing manager | 0 | 80.8 | 0 | 0 | 0
9 | ninth |  | 5FS;8FS | FS10 | 2018-06-08 08:00 | 2018-06-16 08:00 | 9d | Database administrator | 0 | 0 | 0 | 0 | 0
10 | tenth |  | 4FS |  | 2018-06-16 08:00 | 2018-06-25 08:00 | 10d | Technicians[0.75 #3] | 0 | 220 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Programmers | Renewable | 3 Programmers | 0 | 17 | 10;11[1.50 Programmers];16[2.00 Programmers];17[2.50 Programmers];18[2.00 Programmers];19[3.00 Programmers];20[2.00 Programmers];21[3.00 Programmers];31[2.00 Programmers];32; | 4845
2 | IT Manager | Renewable | 1 IT Manager | 0 | 29 | 1[0.20 IT Manager];39[0.10 IT Manager];40[0.10 IT Manager];28;29[0.50 IT Manager];34;35[0.50 IT Manager]; | 493
3 | Database administrator | Renewable | 1 Database administrator | 0 | 19 | 4;5[0.50 Database administrator];6;8;9;12[0.40 Database administrator];13[0.60 Database administrator];14[0.40 Database administrator];15[0.60 Database administrator];31[0.30 Database administrator]; | 1103.9
4 | Analyst programmer | Renewable | 1 Analyst programmer | 0 | 19 | 1;2;3;5[0.50 Analyst programmer];7[0.30 Analyst programmer];27[0.30 Analyst programmer];28;31[0.10 Analyst programmer];33[0.20 Analyst programmer];34; | 1084.9
5 | Secretary | Renewable | 1 Secretary | 0 | 11 | 37;27;33; | 286
6 | Marketing manager | Renewable | 1 Marketing manager | 0 | 30 | 39[0.50 Marketing manager];40[0.50 Marketing manager];37[0.50 Marketing manager]; | 510
7 | Sales representatives | Renewable | 2 Sales representatives | 0 | 15 | 38[2.00 Sales representatives]; | 2400
8 | Technicians | Renewable | 3 Technicians | 0 | 13 | 36[3.00 Technicians];41;42; | 2600

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Commercial IT Project | 453h |  |  |  |  | 99 | 100 | 101
22 | Explore the market | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Set up a survey | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Analysis of the market | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
1 | Problem study/analysis | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Negotiate and buy server | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Negotiate and buy computer | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Processmodels (BPMN) | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Conceptual datamodel (ER) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Normalisation DB | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Datamap | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Logic Databasemodel | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Software design (UML-class diagram) | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Develop Database Tables 1 | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Develop Database Tables 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Design & Develop GUI 1 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Design & Develop GUI 2 | 21h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Design CD-box | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Design CD-labels | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Develop SQL's 1 | 18h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Develop SQL's 2 | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Debug SQL’s 1 | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Debug SQL’s 2 | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Implement SQL’s in JAVA 1 | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Implement SQL’s in JAVA 2 | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Develop program 1 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Develop program 2 | 29h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Testing & Debugging 1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Testing & Debugging 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Visitations by sales representatives | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Direct mailings | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Make up report + presentation Alpha version | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Presentation Alpha version | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Reading of management report + Approval Alpha | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Testing phase Alpha version | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | Fix outstanding problems from Alpha | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Make up Report+ presentation Beta version | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | Presentation Beta version | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Reading of management report + Approval Beta | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Launch and installation Beta version | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Installation server | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Installation computer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3